## Description
Description of the Project
The One Stop Degree Issuance System, is an addition in the Fast University’s main portal to facilitate the students who are interested in sending a degree issuance request to the university’s administration. This software facilitates the students who want to submit a form to generate their degree after their graduation. The main scope of this software covers interested students, (Admin, FYP and Finance Department), along with director to view and maintain the optimal working of this software. The main purpose for the creation of this software was to eradicates the need to physically visit the One Stop Office and convert the entire Degree Issuance Process into an online one.

## Product Backlog
Product Backlog
User Stories
Situation | Name | Description
Done | Submit Degree Issuance Form | As a Student, I want to submit my Degree Issuance Form, so that I can request the university administration to start the process of my degree issuance.
Done | Submit Student Complaint Forms | As a Student, I want to fill a Complaint Form, so that I can file my desired complaint to the university administration regarding my degree issuance process
Done | Submit Student Data Change Form | As a Student, I want to submit my Student’s Data Change Form, so that I provide the university administration with my updated data that has been requested for a change
Done | Submit Student Feedback | As a Student, I want to submit my Feedback Form, so that I can provide my comments regarding the usability of this system.
Done | Track Activity | As a Student, I want to track my Generated Requests, so that I stay updated about my Degree Issuance process.
Done | Receive Student Notification for Degree Issuance | As an Admin, I want to receive student’s notification for Degree Issuance, so that I can address the student’s request of Degree Issuance related to Finance Department.
Done | Update Student Data | As an Admin, I want to receive student’s data change request form, so that I can update the student’s data that was previously incorrect.
Done | View Requests Log | As an Admin, I want to view the Requests Log, so that I can view all the requests received from the students that are either processed, pending or in new state.
Done | Generate Tokens | As an Admin, I want to Generate a Token, so that I can assign a unique id and required time for every student’s request.
Done | Respond to Requests | As an Admin, I want to reply to a student’s requests, so that I can inform the student about any objection on their request from the FYP or Finance Department.
Done | Issue Degree | As an Admin, I want to issue a degree, so that I can complete the student’s request for degree issuance and update the processed request list.
Done | Receive Student Notification for Degree Issuance. | As a Member of the FYP Department, I want to receive student’s Notification for Degree Issuance from the administration, so that I can address the student’s request for Degree Issuance related to the Finance Department.
Done | Process Request | As a Member of the FYP Department, I want to provide my decision regarding the student’s request, so that I can reply back to the student’s request as accepted, rejected or objection.
Done | Process User Complaints | As a Member of the FYP Department, I want to receive student complaints, so that I can resolve the complaints and reply back to the concerned.
Done | View Requests Stats | As a Member of the FYP Department, I want to View Requests Stats, so that I can analyze the time taken by the FYP committee to process a request.
Done | Generate Ineligible Students List | As a Member of the FYP Department, I want to Generate an Ineligible Students List, so that I can notify all the students that are ineligible for Degree Issuance due to issues in their final year project.
Done | Receive Student Notification for Degree Issuance. | As a Member of the Finance Department, I want to receive student’s Notification for Degree Issuance from the administration, so that I can address the student’s request for Degree Issuance related to the Finance Department.
Done | Check Outstanding Dues | As a Member of the Finance Department, I want to view students’ fee details, so that I can check whether all the outstanding dues have been paid or not.
Done | Check Degree Issuance Fee Status | As a Member of the Finance Department, I want to check student’s degree issuance fee status, so that I can check whether the student has paid the degree issuance fee or not.
Done | Process Request | As a Member of the Finance Department, I want to provide my decision regarding the student’s request, so that I can reply back to the student’s request as accepted, rejected or objection.
Done | Issue Transcript | As an Admin, I want to issue a student’s transcript, so that I can provide the student with his/her transcript containing their department, CGPA, all courses’ grades, duration and photograph.
Done | Notify Complaint Result | As an Admin, I want to notify the student of their complaint result, so that I update the student on the outcome of their submitted complaint.
Done | Generate Outstanding Dues List | As a Member of the Finance Department, I want to Generate an Outstanding Dues List, so that I can notify all the students that are ineligible for Degree Issuance because they have encountered an issue related to the clearance of their remaining dues.
Done | View Requests Log | As a Director, I want to view the Requests Log, so that I can view all the requests that were generated on a certain day.
Done | Pending requests | As a Director, I want to view the Requests Log, so that I can view all the students’ requests that are in the pending state.
Done | Processed request | As a Director, I want to view the Requests Log, so that I can view all the students’ requests that are in processed state.
Done | Track Activity | As a Director, I want to track a certain request, so that I can view the status of that request and check in which department the current request is being processed.
Done | View Department Stats | As a Director, I want to View the Request Stats, so that I can analyze the time taken by each department to process the requests.
Done | View Feedback | As a Director, I want to view the submitted feedbacks, so that I check what are the views of students regarding the usability of this system.
Done | View Complaint Forms | As a Director, I want to View all the submitted Complaint Forms, so that I analyze what are the issues that students are currently facing regarding their degree issuance process.

## Sprint 1
BURNDOWN CHART SPRINT 1
Project |  | Story | Beginning | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | Start Date | End Date | Story | Start Date | Task Duration(Days)
One Stop Degree Issuance |  | Submit Degree Issuance Form | 12 | 10 | 8 | 7 | 7 | 6 | 5 | 5 | 3 | 0 | 0 | 2024-04-11 | 2024-04-20 | Submit Degree Issuance Form | 0 | 9
One Stop Degree Issuance |  | Submit Student Complaint Forms | 17 | 15 | 11 | 8 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 2024-04-11 | 2024-04-18 | Submit Student Complaint Forms | 0 | 7
One Stop Degree Issuance |  | Submit Student Data Change Form | 10 | 8 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2024-04-11 | 2024-04-15 | Submit Student Data Change Form | 0 | 4
One Stop Degree Issuance |  | Submit Student Feedback | 8 | 8 | 8 | 6 | 4 | 3 | 3 | 1 | 0 | 0 | 0 | 2024-04-11 | 2024-04-20 | Submit Student Feedback | 0 | 9
One Stop Degree Issuance |  | Track Activity | 8 | 8 | 8 | 5 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 2024-04-11 | 2024-04-21 | Track Activity | 0 | 10
One Stop Degree Issuance |  | Receive Student Notification for Degree Issuance | 14 | 14 | 14 | 14 | 10 | 10 | 8 | 6 | 4 | 4 | 4 | 2024-04-14 | 2024-04-21 | Receive Student Notification for Degree Issuance | 3 | 7
One Stop Degree Issuance |  | Update Student Data | 8 | 8 | 8 | 8 | 6 | 5 | 3 | 2 | 1 | 0 | 0 | 2024-04-14 | 2024-04-20 | Update Student Data | 3 | 6
One Stop Degree Issuance |  | View Requests Log | 6 | 6 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-14 | 2024-04-16 | View Requests Log | 3 | 2
One Stop Degree Issuance |  | Generate Tokens | 11 | 11 | 11 | 11 | 9 | 4 | 3 | 2 | 0 | 0 | 0 | 2024-04-14 | 2024-04-19 | Generate Tokens | 3 | 5
One Stop Degree Issuance |  | Respond to Requests | 8 | 8 | 8 | 8 | 6 | 6 | 5 | 2 | 1 | 0 | 0 | 2024-04-14 | 2024-04-20 | Respond to Requests | 3 | 6
One Stop Degree Issuance |  | Issue Degree | 12 | 12 | 12 | 12 | 9 | 6 | 5 | 2 | 1 | 1 | 1 | 2024-04-14 | 2024-04-21 | Issue Degree | 3 | 7
| Ideal - Remaining time working hours |  | 114 | 102.6 | 91.2 | 79.8 | 68.4 | 57 | 45.6 | 34.2 | 22.8 | 11.4 | 0
| Actual - Remaining time working hours |  | 114 | 96 | 88 | 77 | 56 | 41 | 29 | 19 | 10 | 6 | 6
Note on E5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on F5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered

## Sprint 2
BURNDOWN CHART SPRINT 2
Project |  | Story | Beginning | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | Start Date | End Date | Story | Start Date | Task Duration(Days)
One Stop Degree Issuance |  | Receive Student Notification for Degree Issuance. | 10 | 10 | 8 | 8 | 6 | 5 | 4 | 3 | 2 | 0 | 0 | 2024-04-21 | 2024-04-29 | Receive Student Notification for Degree Issuance. | 0 | 8
One Stop Degree Issuance |  | Process Request | 13 | 10 | 8 | 7 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 2024-04-21 | 2024-04-28 | Process Request | 0 | 7
One Stop Degree Issuance |  | Process User Complaints | 10 | 9 | 6 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 2024-04-21 | 2024-04-25 | Process User Complaints | 0 | 4
One Stop Degree Issuance |  | View Requests Stats | 8 | 8 | 6 | 5 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 2024-04-21 | 2024-04-28 | View Requests Stats | 0 | 7
One Stop Degree Issuance |  | Generate Ineligible Students List | 9 | 8 | 8 | 5 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 2024-04-21 | 2024-04-30 | Generate Ineligible Students List | 0 | 9
One Stop Degree Issuance |  | Receive Student Notification for Degree Issuance. | 12 | 12 | 12 | 12 | 10 | 8 | 6 | 3 | 1 | 0 | 0 | 2024-04-23 | 2024-04-29 | Receive Student Notification for Degree Issuance. | 2 | 6
One Stop Degree Issuance |  | Check Outstanding Dues | 10 | 10 | 10 | 10 | 6 | 0 | 11 | 9 | 1 | 0 | 0 | 2024-04-23 | 2024-04-29 | Check Outstanding Dues | 2 | 6
One Stop Degree Issuance |  | Check Degree Issuance Fee Status | 8 | 8 | 8 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-23 | 2024-04-25 | Check Degree Issuance Fee Status | 2 | 2
One Stop Degree Issuance |  | Process Request | 11 | 11 | 11 | 11 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 2024-04-23 | 2024-04-26 | Process Request | 2 | 3
One Stop Degree Issuance |  | Issue Transcript | 10 | 10 | 10 | 10 | 7 | 7 | 6 | 4 | 2 | 1 | 0 | 2024-04-23 | 2024-04-30 | Issue Transcript | 2 | 7
One Stop Degree Issuance |  | Notify Complaint Result | 10 | 10 | 10 | 10 | 9 | 6 | 5 | 2 | 1 | 1 | 0 | 2024-04-23 | 2024-04-30 | Notify Complaint Result | 2 | 7
| Ideal - Remaining time working hours |  | 111 | 99.9 | 88.8 | 77.7 | 66.6 | 55.5 | 44.4 | 33.3 | 22.2 | 11.1 | 0
| Actual - Remaining time working hours |  | 111 | 106 | 97 | 90 | 68 | 42 | 38 | 24 | 8 | 3 | 0
Note on E5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on F5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered

## Sprint 3
BURNDOWN CHART SPRINT 3
Project |  | Story | Beginning | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | Start Date | End Date | Story | Start Date | Task Duration(Days)
One Stop Degree Issuance |  | Generate Outstanding Dues List | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-01 | 2024-05-03 | Generate Outstanding Dues List | 0 | 2
One Stop Degree Issuance |  | View Requests Log | 8 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-02 | 2024-05-04 | View Requests Log | 1 | 2
One Stop Degree Issuance |  | Pending requests | 5 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-02 | 2024-05-04 | Pending requests | 1 | 2
One Stop Degree Issuance |  | Processed request | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-02 | 2024-05-05 | Processed request | 1 | 3
One Stop Degree Issuance |  | Track Activity | 8 | 5 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-02 | 2024-05-05 | Track Activity | 1 | 3
One Stop Degree Issuance |  | View Department Stats | 5 | 5 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-03 | 2024-05-05 | View Department Stats | 2 | 2
One Stop Degree Issuance |  | View Feedback | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-03 | 2024-05-04 | View Feedback | 2 | 1
One Stop Degree Issuance |  | View Complaint Forms | 6 | 6 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-03 | 2024-05-05 | View Complaint Forms | 2 | 2
| Ideal - Remaining time working hours |  | 45 | 40.5 | 36 | 31.5 | 27 | 22.5 | 18 | 13.5 | 9 | 4.5 | 0
| Actual - Remaining time working hours |  | 45 | 39 | 27 | 12 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Note on E5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on F5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered